## 시트1
Schedule | Type | Plan | Detail
1w | both | sharing idea for game
2w | both | preparing for 1st milstone
1st milestone
3w | server | Sharing git repository
Building a server
| client | Implementing game frame
|  | Creating key game objects | Player, Obstacle, Board, Tile
4w | both | Implementing game logic | Algorithm for Player
5w | both | Implementing game logic | Algorithm for Obstacle
6w | server | Synchronization | Communication between sever and users
| client | Implementing game logic | Timer function
Algorithm for winning condition
7w | server | Synchronization | Communication between sever and users
| client | Implementing user interface | Tile visualization
| both | Preparing for 2nd milestone
2nd milestone
8w | server | Implementing Sign in/Log in service
| client | Implementing user interface | Game scenes, visual UI, sound effects
9w | server | Implementing database system | User profile
| client | Implementing user interface | Game scenes, visual UI, sound effects
10w | server | Implementing database system | User winning rate
| client | Implementing additional stages
11w,12w | both | Complementing final version of game
Preparing for 3rd milestone
3rd milstone